GONKA ROUTER  |  AI FOR SOCIETY

Hackathon Product Backlog
and Execution Plan

Team Tenners | Working product: Anxin

A bilingual English-Chinese scam and misinformation checker, with meme explanation as an accessibility extension.

| PLAN | VALUE | PLAN | VALUE |
| --- | --- | --- | --- |
| Build window | 2-5 September 2026 (MYT) | Submission | 5 September, 11:59 PM MYT |
| Internal target | Submit by 8:00 PM MYT | Pitch day | 6 September 2026 at APU |
| Team model | Four registered people total | Pitch format | 3 min + 1 min Q&A |

Placement strategy: Win confidence with a reliable live vertical slice: real evidence, two pinned Gonka models, honest disagreement handling, and public Request-ID receipts. Polish only after that loop works end to end.

Roster assumption: This plan assumes four registered people total. If 'four teammates' means five people including the lead, resolve the team-size violation with MUBA immediately.

# 1. TL;DR - tasks to complete

- Confirm the four-person roster, Devfolio registration and APU attendance.

- Set up the GitHub repository, issue board, branches, reviews, .gitignore and secret handling.

- Freeze Anxin's English-Chinese scope, user flow, API contract and result format.

- Smoke-test MiniMax and DeepSeek; capture Request IDs, shard IDs and public receipts.

- Build the FastAPI backend and two-model Gonka verification pipeline.

- Implement consensus scoring, disagreement handling, evidence and receipt lookup.

- Build the responsive bilingual frontend and Anxin result screens.

- Add approved local OCR with an editable text preview for screenshots.

- Complete scam/risk checking first, then add text-based meme explanation.

- Test English, Chinese, accessibility, security, failures and mobile layouts.

- Deploy the frontend and backend; run production smoke tests and prepare backups.

- Create Anxin's user-flow, internal-process and UML/class diagrams from the working implementation.

- Finish the README, licences, AI-use disclosure, slides, video, pitch and Q&A notes.

- Audit Devfolio fields and links, then submit early and rehearse the live demo.

# 2. Confirmed scope and non-negotiables

| Area | Decision |
| --- | --- |
| Core public value | Help ordinary users, especially older adults, understand scams and questionable claims in English and Simplified Chinese. |
| Required inference | All AI reasoning and verification runs through Gonka Router; development assistants do not power the deployed product. |
| Transparency | Display the Gonka X-Request-Id for each inference step and link to the public receipt endpoint. |
| Model independence | Use Gonka-recommended MiniMax-M2.7 and DeepSeek with X-Gonka-No-Fallback: true; do not depend on unstable Kimi for the demo. |
| Output | Truth Score, evidence, understandable reasoning summary, uncertainty, next actions and model metadata. |
| Screenshot boundary | Gonka approved local OCR for text extraction. All classification, reasoning, verification and explanation still run through Gonka Router. |
| Secondary scope | Meme explanation is valuable but cannot delay the working fact-check flow. |
| Blockchain | Gonka confirmed no separate testnet smart contract is required; Request IDs are sufficient. |
| Submission | Public repository, README, live URL, 2-5 minute video, Devfolio package and a three-minute physical pitch plus one-minute Q&A. |

## 2.1 Latest organizer Q&A clarifications

| Topic | Operating rule |
| --- | --- |
| Pitch format | One physical judging round only: 3 minutes to pitch and 1 minute for Q&A. Winners also depend on submitted materials and prototype references. |
| Pitch logistics | First-come-first-served within allocated sessions: 10:00 AM-1:00 PM and 2:00 PM-5:00 PM. Arrive early and expect parallel track rooms. |
| Attendance | At least one representative must pitch; the Q&A also calls APU attendance compulsory for participants. Plan for all four to attend and seek a written exception if needed. |
| Demo video | MUBA confirmed that 2-5 minutes is accepted. Show how the coded prototype solves the problem and aligns with the track; team members do not need to appear on camera. |
| OCR permission | Gonka confirmed that local Tesseract or PaddleOCR may extract screenshot text before Gonka performs all classification, reasoning and explanation. |
| AI and reuse | AI coding tools are allowed without judging penalty when disclosed. Existing projects/repos may be reused only when improvements are clarified, justified and proved; direct copying is not allowed. |
| Deployment | General deployment is not mandatory, but a coded demo is expected. Because the Gonka brief asks for a live URL, deployment remains a P0 placement target. |
| Mentoring | Track validation can be requested before submission by tagging Carol/Gonka mentors. No project changes are allowed after submission closes. |
| Event readiness | Proper attire and covered shoes are required. Carry device, power, hotspot and offline demo backups. |

# 3. Four-person ownership model

| Code | Role | Primary ownership | Accountability |
| --- | --- | --- | --- |
| LEAD | Product and integration lead | Scope, backlog, API contract, consensus rules, integration, submission | Unblocks decisions; reviews all P0 merges |
| BE | Backend and Gonka lead | FastAPI, GonkaClient, local OCR boundary, evidence, verifier orchestration, receipts, deployment | Owns reliable end-to-end API |
| FE | Frontend and UX lead | Next.js, bilingual design, accessibility, results, responsiveness | Owns user-visible quality and live demo |
| QA/DOCS | Quality, documentation and pitch lead | Tests, security checks, README, licences, video, slides, rehearsals | Owns proof that the product works and is understood |

Working rule: one primary owner per backlog item, one reviewer, and no simultaneous editing of the same file without coordination.

# 4. Dated execution plan

| Date | Focus | Work | Exit criterion |
| --- | --- | --- | --- |
| 2 Sep | Foundation + proof | Roster/repo; smoke tests; API schema; two-model vertical slice | A real report with two Request IDs and receipt links |
| 3 Sep | Complete core product | Evidence; consensus; bilingual input/results; errors; first deployment | P0 workflow works from public URL |
| 4 Sep | Reliability + differentiation | Tests; accessibility; approved local OCR; text-based meme mode; diagrams; README; slide draft | Release candidate and recorded backup demo |
| 5 Sep | Submission day | Production QA; video; final README; rehearsals; Devfolio audit | Submit by 8:00 PM MYT, not 11:59 PM |
| 6 Sep | Pitch day | Arrive early; final smoke test; device/network backup; 3-minute pitch + 1-minute Q&A | Clear proof in 180 seconds and direct answers in 60 seconds |

# 5. General hackathon process flowchart

This is the team's delivery sequence. The Anxin user-flow, internal-process and UML diagrams are backlog tasks to create after the relevant implementation is working.

Figure 1. General hackathon delivery process from scope to pitch.

# 6. Engineering approach and standards

## 6.1 Architecture

Frontend: Next.js + TypeScript, accessible functional components and a small shared design system.

Backend: FastAPI + Pydantic, with small service classes and dependency injection where it improves testability.

Screenshot preprocessing: Tesseract or PaddleOCR extracts English/Chinese text locally and never determines meaning, risk or truth; users can correct its output.

Inference: pinned DeepSeek and MiniMax calls through Gonka Router, executed concurrently and recorded separately.

Evidence: retrieval is separate from judgement; every source carries a URL, title and extraction timestamp.

Diagram task: After the vertical slice is working, create Anxin's user journey flowchart, internal processing flowchart and UML/class responsibility diagram. Base all three on the real implementation and then reuse them in the README and slides.

## 6.2 Coding standards

| Area | Standard |
| --- | --- |
| Python | Type hints; Pydantic schemas; Ruff formatting/linting; Pyright; small testable services. |
| TypeScript | Strict mode; ESLint; functional React components; typed API client; no any without justification. |
| Design | Semantic HTML; keyboard support; readable Chinese typography; warnings never depend on colour alone. |
| Security | Server-only keys; no sensitive input logs; safe URL fetching; upload limits; sanitized untrusted content. |
| Review | At least one teammate reviews every P0 pull request; tests and checks must pass before merge. |
| Scope | Prefer the simplest correct implementation. Do not add authentication, databases or blockchain without a validated need. |

# 7. Full product backlog

Priority: P0 = must ship; P1 = strong placement feature; P2 = only after every P0 passes. Story points: 1, 2, 3, 5 and 8 represent relative effort/uncertainty, not hours.

Scope gate: A P1 or P2 item may start only when it cannot endanger the P0 vertical slice, deployment, documentation, video or pitch.

## Epic 0 - Compliance, scope and coordination

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| ADM-01 | Confirm exactly four registered members total; registration, LinkedIn and APU attendance | P0 | LEAD | 1 | Roster is valid and every member can meet event obligations. |
| ADM-02 | Freeze one-sentence problem, target users and success metric | P0 | ALL | 2 | All members can repeat the same product statement and demo outcome. |
| ADM-03 | Archive the opening Q&A and MUBA/Gonka clarifications on AI tools, OSS components, OCR, video length and no smart contract | P0 | DOCS | 1 | Source files, screenshots and dated notes are saved in the team workspace. |
| ADM-04 | Create public competition repository and protect secrets | P0 | LEAD | 2 | Repository history is compliant; .env and keys are ignored. |
| ADM-05 | Create board, milestones and daily 15-minute stand-up | P0 | LEAD | 2 | Every P0 item has an owner, status and target date. |
| ADM-06 | Record licences and AI-assisted-development disclosure | P0 | DOCS | 2 | README and THIRD_PARTY_NOTICES identify actual tools/components used. |
| ADM-07 | Request a pre-submission idea and demo review from the Gonka mentor | P1 | LEAD | 2 | Feedback from Carol or the track team is recorded and resolved before submission. |
| ADM-08 | Confirm pitch-day attendance, presenter, arrival plan and proper attire | P0 | ALL | 2 | All four plan to attend APU; one presenter is designated; covered shoes and transport are confirmed. |

## Epic 1 - Architecture and engineering foundation

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| ARC-01 | Initialize Next.js/TypeScript frontend and Python/FastAPI backend | P0 | FE+BE | 3 | Both applications start locally from documented commands. |
| ARC-02 | Define folders, naming conventions and ownership boundaries | P0 | LEAD | 2 | Architecture supports parallel work without duplicate responsibilities. |
| ARC-03 | Define typed request/response schemas before UI integration | P0 | BE+FE | 3 | Frontend and backend agree on a versioned verification report schema. |
| ARC-04 | Configure formatting, linting, type checking and pre-commit checks | P0 | QA | 3 | Ruff/Pyright and ESLint/TypeScript checks run without errors. |
| ARC-05 | Create CI workflow for lint, types and tests | P1 | QA | 3 | Every pull request receives an automated pass/fail result. |
| ARC-06 | Create Anxin's user-flow and internal-processing flowcharts, plus its UML/class diagram | P1 | ALL | 5 | All three diagrams match the working implementation and show the user journey, technical sequence and real class/service responsibilities. |

## Epic 2 - Gonka Router integration and verifiability

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| GON-01 | Run authenticated smoke tests against MiniMax and DeepSeek | P0 | BE | 2 | Both return HTTP 200 and real response content. |
| GON-02 | Implement GonkaClient with server-side secret loading | P0 | BE | 3 | No key reaches browser, logs or repository. |
| GON-03 | Pin verifier models with X-Gonka-No-Fallback: true | P0 | BE | 2 | Saturation returns 429 rather than silently changing model identity. |
| GON-04 | Capture requested/actual model, X-Request-Id, X-Devshard-ID and fallback header | P0 | BE | 3 | Every inference result includes complete transparency metadata. |
| GON-05 | Run DeepSeek and MiniMax verification concurrently | P0 | BE | 5 | Independent model results arrive under one correlation/report ID. |
| GON-06 | Link each X-Request-Id to the public receipt endpoint | P0 | BE+FE | 2 | Receipt links open and match model, shard, outcome and timing. |
| GON-07 | Handle 429, timeout and partial-result states | P0 | BE | 5 | Users receive bounded retries and honest uncertainty, never a fake success. |
| GON-08 | Add optional deferred hedge after 1.5-2 seconds | P2 | BE | 5 | Same-model duplicate reduces tail latency without replacing second opinion. |
| GON-09 | Measure five calls per model and select stable demo settings | P1 | QA+BE | 3 | Team records success rate, median and slowest response time; Kimi is excluded while unstable. |

## Epic 3 - Fact-checking and consensus pipeline

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| VER-01 | Validate text, URL and mode inputs | P0 | BE | 3 | Invalid or excessive input is rejected with actionable errors. |
| VER-02 | Extract atomic verifiable claims through Gonka | P0 | BE | 5 | Output is structured JSON and separates facts from opinions. |
| VER-03 | Retrieve and normalize relevant evidence with source URLs | P0 | BE | 5 | Report contains attributable evidence rather than unsupported judgement. |
| VER-04 | Protect URL retrieval against SSRF and unsafe content | P0 | BE+QA | 5 | Private/local addresses are blocked; HTML is size-limited and sanitized. |
| VER-05 | Prompt both models independently using identical evidence | P0 | BE | 3 | Neither verifier sees the other verifier's conclusion. |
| VER-06 | Validate model verdicts against a strict Pydantic schema | P0 | BE | 3 | Malformed output is retried or reported; it never breaks the UI. |
| VER-07 | Implement documented consensus and disagreement rules | P0 | LEAD+BE | 5 | Large disagreement returns Uncertain instead of false confidence. |
| VER-08 | Produce Truth Score, risk level and confidence separately | P0 | LEAD+BE | 3 | Score meanings are documented and not confused with scam risk. |
| VER-09 | Generate concise English and Simplified Chinese explanations | P0 | BE+FE | 5 | Both languages describe the same evidence and verdict. |
| VER-10 | Add sources, limitations and recommended next actions | P0 | LEAD+FE | 3 | Result supports safe user action and avoids claiming absolute truth. |
| VER-11 | Create shareable report identifier or URL | P2 | BE+FE | 5 | A report can be revisited without leaking sensitive submissions. |

## Epic 4 - Bilingual, elder-friendly frontend

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| UI-01 | Establish design tokens and accessible component system | P0 | FE | 3 | Typography, colours, spacing and states are consistently reused. |
| UI-02 | Build English/Chinese language switch from day one | P0 | FE | 3 | All core screens switch languages without reload or hardcoded strings. |
| UI-03 | Build text/URL/screenshot input and analysis-mode selector | P0 | FE | 5 | Keyboard and mobile users can submit supported inputs successfully. |
| UI-04 | Create clear progress states for slow decentralized inference | P0 | FE | 3 | Users see current stage, elapsed time and can cancel/retry. |
| UI-05 | Build verdict, Truth Score, risk and evidence hierarchy | P0 | FE | 5 | Most important conclusion is understandable within five seconds. |
| UI-06 | Build expandable model and receipt transparency panel | P0 | FE | 5 | Request IDs, shards, models and receipt links are visible. |
| UI-07 | Implement accessible warnings without colour-only meaning | P0 | FE+QA | 3 | Icons, labels and text accompany red/green status colours. |
| UI-08 | Polish responsive layout at mobile, tablet and desktop widths | P1 | FE | 5 | No overflow or unusable controls at target widths. |
| UI-09 | Add empty, timeout, partial and invalid-input states | P0 | FE | 3 | Every known failure path has understandable recovery guidance. |
| UI-10 | Adapt selected shadcn/21st.dev components with attribution | P1 | FE+DOCS | 3 | Components are licensed, modified and documented. |

## Epic 5 - Image and meme accessibility extension

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| IMG-01 | Validate image type, dimensions and file size | P1 | BE+FE | 3 | Only supported safe files reach the analysis pipeline. |
| IMG-02 | Implement local OCR with Tesseract or PaddleOCR for text extraction only | P1 | BE+QA | 5 | English and Chinese text is extracted without making any classification or judgement outside Gonka. |
| IMG-03 | Show editable OCR text before Gonka analysis | P1 | BE+FE | 3 | Users can review and correct extracted text before submitting it to the verification flow. |
| IMG-04 | Implement text-based meme explanation mode through Gonka | P1 | BE+FE | 5 | Report explains literal wording, joke, slang and cultural/safety context; visual-only memes request a user description. |
| IMG-05 | Ensure meme mode does not imply green equals verified safe | P1 | FE+QA | 2 | Mode styling is distinct while factual claims remain separately assessed. |
| IMG-06 | Document the approved OCR boundary and image limitations | P0 | BE+DOCS | 2 | README states that local OCR only extracts text and all reasoning, verification and explanation run through Gonka. |

## Epic 6 - Testing, security and reliability

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| QA-01 | Unit-test score boundaries and disagreement scenarios | P0 | QA+BE | 5 | Tests cover agreement, conflict, missing evidence and one-model failure. |
| QA-02 | Mock Gonka responses for deterministic integration tests | P0 | QA+BE | 5 | CI does not depend on live credits or network availability. |
| QA-03 | Run live Gonka integration smoke tests | P0 | QA | 3 | Pinned models, headers and public receipts are verified before demo. |
| QA-04 | Create Playwright end-to-end test for the main journey | P0 | QA+FE | 5 | Input-to-report workflow passes on desktop and mobile viewport. |
| QA-05 | Run keyboard, contrast and screen-reader-oriented audit | P1 | QA | 3 | Core experience meets WCAG-minded accessibility expectations. |
| QA-06 | Review secrets, logs, uploads, CORS and input sanitization | P0 | QA+LEAD | 3 | No critical security issue remains; sensitive text is not logged. |
| QA-07 | Prepare graceful live-demo failure strategy | P0 | ALL | 2 | Team has tested input, recorded backup video and transparent recovery path. |

## Epic 7 - Deployment and operations

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| DEP-01 | Deploy frontend and obtain stable public URL | P0 | FE | 3 | Public HTTPS URL loads without authentication; deployment remains the team target even though the general Q&A says it is not mandatory. |
| DEP-02 | Deploy FastAPI backend in a supported runtime | P0 | BE | 5 | Health check and verification endpoint work from production. |
| DEP-03 | Configure production secrets, CORS and environment variables | P0 | BE+LEAD | 3 | Frontend origin works; API key remains server-side. |
| DEP-04 | Add health endpoint and lightweight request correlation logs | P1 | BE | 2 | Team can diagnose demo failures without storing user content. |
| DEP-05 | Run production smoke test on English and Chinese flows | P0 | QA | 3 | Two real reports complete from the public URL. |

## Epic 8 - Documentation, video, presentation and submission

| ID | Backlog item | Priority | Owner | SP | Acceptance / done |
| --- | --- | --- | --- | --- | --- |
| DOC-01 | Write README: problem, solution, architecture and public-value case | P0 | DOCS | 5 | A new reviewer understands the project in under three minutes. |
| DOC-02 | Document setup, environment variables and Gonka integration | P0 | BE+DOCS | 3 | A developer can run both applications without private guidance. |
| DOC-03 | Document no-smart-contract clarification and receipt verification | P0 | DOCS | 2 | README accurately explains Request IDs and proof limitations. |
| DOC-04 | Add AI-use disclosure, licences and third-party notices | P0 | DOCS | 2 | Disclosure matches actual tools/components and source licences. |
| DOC-05 | Disclose and prove improvements if any existing project, repository or component is reused | P0 | DOCS+LEAD | 3 | README, video or pitch clearly distinguishes original work, reused work and hackathon improvements. |
| DOC-06 | Add the finalized Anxin flowcharts and UML diagram to project materials | P1 | DOCS+LEAD | 3 | README and slides use the same current diagrams created from the working implementation. |
| DEMO-01 | Prepare reliable English and Chinese demonstration inputs | P0 | ALL | 2 | Inputs produce concise, visually compelling outcomes. |
| VID-01 | Write the confirmed 2-5 minute video script and shot list | P0 | DOCS | 3 | Script targets roughly 2:30-3:00 and focuses on the coded prototype, track alignment, consensus, evidence and Request IDs; faces are optional. |
| VID-02 | Record, edit, caption and upload demonstration video | P0 | DOCS+FE | 5 | Video is public/unlisted, audible, legible, prototype-focused and within the organizer-confirmed 2-5 minute range. |
| PIT-01 | Create a three-minute presentation | P0 | DOCS+LEAD | 5 | Slides prove the product and Gonka integration within 180 seconds. |
| PIT-02 | Prepare a 60-second Q&A bank | P0 | ALL | 3 | Prepared answers cover product, technical, ethics and reliability. |
| PIT-03 | Run three timed rehearsals with a live-demo failure drill | P0 | ALL | 3 | Pitch consistently finishes below three minutes, leaving the full one minute for Q&A. |
| PIT-04 | Plan pitch-day arrival and backups | P0 | LEAD | 2 | Team arrives early for its assigned session with local and online demo backups. |
| SUB-01 | Audit the Devfolio submission | P0 | LEAD+DOCS | 3 | Every required field and link is verified by two members. |
| SUB-02 | Submit by 8:00 PM MYT on 5 September | P0 | LEAD | 1 | Submission confirmation is archived with a four-hour buffer. |

# 8. Definition of Done

A backlog item is Done only when all relevant conditions below are satisfied:

Behaviour meets its acceptance criterion and the owner can demonstrate it.

Code is formatted, typed and free of new lint errors.

Relevant unit, integration or browser tests pass.

Error and empty states are handled; no raw stack trace reaches users.

Secrets and sensitive user inputs do not appear in commits, frontend bundles or logs.

English and Chinese UI text remains semantically aligned where applicable.

A teammate reviews the change and requested fixes are resolved.

Documentation and diagrams are updated if interfaces or behaviour changed.

The change is committed with a meaningful message and deployed if it affects the release candidate.

# 9. Git and integration plan

## 9.1 Branches

Use main for the submitted release and short-lived feature branches such as feat/gonka-client, feat/verification-ui, feat/consensus, test/e2e and docs/submission. A develop branch is optional; use it only if the team can manage it consistently.

## 9.2 Commit progression

| Type | Example meaningful commit |
| --- | --- |
| chore | initialize frontend, backend and quality tooling |
| docs | add product scope, API contract and architecture |
| feat(api) | add pinned Gonka client and response metadata |
| feat(api) | implement claim extraction, evidence and consensus |
| feat(web) | build bilingual input and verification results |
| test | cover consensus, API failures and the main browser journey |
| feat | add approved local OCR and text-based meme explanation |
| docs | complete README, diagrams, licences and demo instructions |
| fix | resolve production and rehearsal findings |
| release | prepare hackathon submission candidate |

Commit quality: Commit demonstrable increments. Do not manufacture commits, rewrite public history, or squash the project into one final commit.

# 10. Test and release strategy

| Layer | Coverage | Cadence |
| --- | --- | --- |
| Unit | Consensus thresholds, conflicting verdicts, score boundaries, schema validation and OCR text normalization | Every commit affecting logic |
| Mock integration | Gonka timeout, 429, malformed JSON, partial verifier and receipt failure | Every backend pull request |
| Live integration | Pinned model identity, headers, public receipts and latency | Twice daily and before demo |
| Browser | Text input through bilingual report on desktop/mobile | Before each release candidate |
| Accessibility | Keyboard order, focus, labels, contrast, text scaling and non-colour warnings | Daily after UI changes |
| Production | English and Chinese paths from public URL | After every production deployment |

# 11. Demo, video and pitch plan

## 11.1 Live demonstration sequence

- State the user problem in one sentence, then paste one short scam or questionable claim.

- While analysis runs, explain that DeepSeek and MiniMax verify the same evidence independently through Gonka.

- Show the Truth Score, risk warning, sources, uncertainty and recommended next action.

- Open one public receipt link, then switch the report to Chinese. Mention screenshot/meme mode only if it is already stable.

## 11.2 Confirmed demo video plan (2-5 minutes)

Target roughly 2:30-3:00 for a concise edit; the organizer-confirmed acceptable range is 2-5 minutes.

Open with the user problem and one-sentence solution, then spend most of the video on the working prototype.

Show input, two-model verification, evidence, disagreement handling, bilingual output and Gonka Request-ID receipts.

Explicitly connect the prototype to the Gonka Router track and public value for English- and Chinese-speaking users.

Use captions and readable zoom. Team members do not need to appear on camera.

If reused code or an earlier repository is involved, identify the hackathon improvements in the narration or end card.

## 11.3 Three-minute pitch structure

| Time | Section | What judges should remember |
| --- | --- | --- |
| 0:00-0:20 | Problem and user | One relatable scam scenario and why bilingual, elder-friendly explanation matters. |
| 0:20-1:35 | Live demonstration | Input, progress, evidence, two models, consensus, Chinese switch and one receipt. |
| 1:35-2:10 | How it works | Pinned Gonka models, Request IDs, public receipts and honest disagreement handling. |
| 2:10-2:42 | Difference and impact | Neutrality, accessibility, privacy and practical public value. |
| 2:42-3:00 | Close | Memorable value proposition and invitation to verify the receipt. |

## 11.4 One-minute Q&A preparation

Answer rule: Lead with the direct answer in one sentence, then give one proof point. With only 60 seconds, expect one or two questions and stop when the judge has the answer.

Why two models, and how do you know they are actually different?

How is the Truth Score calculated and calibrated?

What happens when evidence is weak or models disagree?

What does the receipt prove, and what does it not prove?

How do you prevent URL attacks, privacy leakage and misleading certainty?

Why is meme explanation part of public value rather than feature creep?

How would the product sustain itself after free hackathon credits?

# 12. Top risks and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Gonka latency/429 | High | Use the recommended MiniMax-M2.7 and DeepSeek; parallel pinned calls; bounded retry; progress UI; tested backup video. |
| Kimi instability | High | Do not depend on Kimi for the core product or judging demo; re-evaluate only after Gonka confirms recovery. |
| Model substitution | High | X-Gonka-No-Fallback: true; record requested and actual model. |
| OCR error | Medium | Display editable extracted text before Gonka analysis; test English and Chinese screenshots; never treat OCR as verification. |
| Visual-only meme | Medium | State the text-only limitation and request a short user description instead of inventing visual context. |
| Evidence quality | High | Prefer attributable independent sources; show limitations and retrieval times. |
| Scope creep | High | P0 gate; meme and sharing remain behind complete fact-check/deployment/doc work. |
| Three-minute overrun | High | Time every rehearsal; pre-load the demo; one speaker controls pacing; cut extension features before cutting Gonka proof. |
| Five-person roster | Critical if applicable | Confirm four total registered members immediately; do not use undeclared collaborators. |
| Pitch-day attendance | High | Plan for all four at APU; designate at least one presenter; confirm transport, session, attire and covered shoes. |
| Secret exposure | Critical | Server-only key, .env ignored, secret scan before every release. |
| Demo internet failure | Medium | Hotspot, pretested input, cached static screenshots only as clearly labelled backup, and video. |
| Chinese inconsistency | Medium | Shared locale keys; native-speaker review if available; bilingual acceptance tests. |
| Unlicensed component | Medium | Use identifiable OSS sources; retain licences and document modifications. |

# 13. Final submission checklist

| Deliverable | Completion test | Owner |
| --- | --- | --- |
| Repository | Public, compliant history, no secrets, stable main branch, release tag and reuse/improvement disclosure if applicable | LEAD |
| Application | Public HTTPS URL; production English/Chinese fact-check succeeds | FE+BE |
| Gonka proof | Two pinned models; Request IDs; shard IDs; working public receipt links | BE+QA |
| Quality | Unit/mock/live/browser/accessibility/security checks completed | QA |
| README | Problem, setup, architecture, Gonka integration, approved OCR boundary, no-contract note, limitations and team | DOCS |
| Attribution | AI-use disclosure and third-party licences match actual usage | DOCS |
| Video | Organizer-confirmed 2-5 minutes; target 2:30-3:00; prototype-focused; captions legible; link works incognito; faces optional | DOCS |
| Screenshot/OCR | Local OCR extracts text only; output is editable; all meaning, risk, verification and explanation run through Gonka | BE+QA |
| Pitch | 3 minutes + 1 minute Q&A; speakers assigned; three rehearsals and failure drill | ALL |
| Event | All four plan to attend APU; presenter, transport, session, attire, covered shoes and backups confirmed | ALL |
| Devfolio | Every field/link checked by two people; submitted by 8:00 PM MYT | LEAD / DOCS |
| Evidence | Submission confirmation and organizer clarifications archived | LEAD |

# 14. Source references

Gonka Router challenge brief supplied by the organizers (AI for Society).

MUBA Opening Ceremony QnA, five-page organizer document supplied to Team Tenners.

MUBA Discord rules and organizer clarifications archived by Team Tenners.

MUBA and Gonka Discord clarification, 2 September 2026: 2-5 minute demo video accepted and local OCR permitted for text extraction.

Gonka Discord model-status guidance, 2 September 2026: prioritize MiniMax-M2.7 and DeepSeek while Kimi remains unstable.

Gonka integration guide: https://gonkarouter.io/docs

Gonka model catalogue: https://gonkarouter.io/models

Public receipt pattern: https://api.gonkarouter.io/v1/receipts/{x-request-id}